## Dashboard
Programme Budget — Atlas Migration
Atlas Migration · prepared 19 October 2026 · USD
Total budget |  | Actual spend |  | Variance |  | Used
Approved envelope |  | Committed to date |  | Positive is under budget |  | Of approved envelope
Workstream budget and actuals
Workstream | Budget | Actual | Variance | Used % | Hours | Owner
Discovery and design | 26346 | 25292 |  |  | 320 | M. Lindqvist
Platform build | 58338 | 60671 |  |  | 1180 | O. Price
Data migration | 33874 | 29809 |  |  | 640 | D. Osei
Integration | 22582 | 25291 |  |  | 410 | S. Alvarez
Testing and QA | 16937 | 15582 |  |  | 290 | P. Raman
Training | 9409 | 6962 |  |  | 160 | M. Lindqvist
Rollout | 11291 | 12194 |  |  | 210 | O. Price
Contingency | 9409 | 1881 |  |  | 0 | Finance
Reserve 0 | 0 | 0 |  |  | 0 | Finance
Reserve 1 | 0 | 0 |  |  | 0 | Finance
Reserve 2 | 0 | 0 |  |  | 0 | Finance
Reserve 3 | 0 | 0 |  |  | 0 | Finance
Total

## Trend
Budget used by workstream
Workstream | Budget used
Discovery and design
Platform build
Data migration
Integration
Testing and QA
Training
Rollout
Contingency
Reserve 0
Reserve 1
Reserve 2
Reserve 3

## Data
Workstream budget and actuals
Edit Budget and Actual; the dashboard and variance recalculate.
Workstream | Budget | Actual | Variance | Used % | Hours | Owner | Notes
Discovery and design | 26346 | 25292 |  |  | 320 | M. Lindqvist | Planned
Platform build | 58338 | 60671 |  |  | 1180 | O. Price | In flight
Data migration | 33874 | 29809 |  |  | 640 | D. Osei | Under review
Integration | 22582 | 25291 |  |  | 410 | S. Alvarez | Change request
Testing and QA | 16937 | 15582 |  |  | 290 | P. Raman | Planned
Training | 9409 | 6962 |  |  | 160 | M. Lindqvist | Complete
Rollout | 11291 | 12194 |  |  | 210 | O. Price | Planned
Contingency | 9409 | 1881 |  |  | 0 | Finance | Held
Reserve 0 | 0 | 0 |  |  | 0 | Finance | Held
Reserve 1 | 0 | 0 |  |  | 0 | Finance | Held
Reserve 2 | 0 | 0 |  |  | 0 | Finance | Held
Reserve 3 | 0 | 0 |  |  | 0 | Finance | Held

## Assumptions
Assumptions and controls
Contingency held | 10%
Forecast uplift | 8%
Cost inflation | 4%
Working days / month | 21
Approval threshold | 25000
Notes
All values are fictional and internally consistent for demonstration.
Dashboard totals use live formulas; edits in Data recalculate the view.
No external links, macros or cached secrets are present in this workbook.
Workbook mode: budget; chart series are bound to the table above.